## Slide 1: Odoo ERP
Koko Settlements and Payment System Overview

## Slide 2: Primary Objective:
Business Analysis and Knowledge Transfer of KN Processes to Prolitus
KN Financial Processes in Odoo - Simulation Data
System Gap Analysis - Identification of Gaps
Gap Analysis Report - System Design
API Analysis
Implementation
QA Testing
User Training
User Acceptance Test
Go Live

## Slide 3: Secondary Objective:
Odoo Purchasing, Sales & Accounting Module
  Configuration
  Update of Chart of Accounts
  User Training and Go Live (Training Provided - additional sessions required)
Odoo CRM & Agent Inspection Application - User Training and Go Live
  Development & Testing
  Migration of Opportunity Information
  User Training and Go Live (Awaiting Training Schedule)

## Slide 4: Current Status
Task | Description | Status | Date of Completion
Business Analysis | Knowledge Transfer of KN Accounting and Finance processes for KSPS. Detailed descriptions of workflows and JE’s providing reasons for processes and ensuring partner understands these clearly. | Complete | 09 August 2018
Simulation Data - Odoo Screenshots | Entering workflow dummy data into the ERP system to Identify gaps in the system (for development). Providing Screenshots of dummy data to end users for clarification on any additional document added in the process. | Complete | 02 August 2018
System Gap Analysis | Identification of System Gaps which assist in building case for development. Decisions are made on if Gaps can be configured, customised or built. | Complete | 10 August 2018
Gap Analysis Report & System Design | A Gap Analysis Report is created from the System Gaps Identified, This is also defined as a System Design, where Development Tasks and Efforts are defined, for additional configuration and customisation. | Ongoing | 17 August 2018
API Analysis and Signature Document | Identification of API requirements for KOKO Core and Odoo Transactional Data and Master Data | Pending | 24 August 2018
Implementation - Workflow; Customer Buys Credit & Customer Buys Product - Smartcook Stove | Implementation of pre-configurations and customised elements for workflows | Ongoing | 17 August 2018 (No API Integration at this stage)

## Slide 5
Task | Description | Status | Date of Completion
Implementation - Workflow; Customer Buys Fuel & Agent Buys KN Franchise (Pending Discussion on Change Management). | Implementation of pre-configurations and customised elements for workflows | Pending | 28 August 2018
Implementation - Workflow; Agent Loan Management System & Agent Buys Fuel from Wholesaler. | Implementation of pre-configurations and customised elements for workflows | Pending | 12 September 2018
Implementation - Workflow; Loan Payable to Bank & Customer Credit Transfer. | Implementation of pre-configurations and customised elements for workflows | Pending | 18 September 2018
Implementation Workflow; Outgoing Payment & Reconciliation- Fuel Wholesaler Payments. | Implementation of pre-configurations and customised elements for workflows | Pending | 25 September 2018
Implementation Workflow - Outgoing Payment & Reconciliation - KN Agent Payments for Commissions and Margin. | Implementation of pre-configurations and customised elements for workflows | Pending | 27 September 2018
Implementation Workflow - Outgoing Payment & Reconciliation - Kenya Revenue Authority | Implementation of pre-configurations and customised elements for workflows | Pending | 28 September 2018

## Slide 6
Task | Description | Status | Date of Completion
Implementation - Workflow; Outgoing Payment - Loan Repayment to Bank | Implementation of pre-configurations and customised elements for workflows | Pending | 2 October 2018
Code Review & System Testing | Implementation of pre-configurations and customised elements for workflows | Pending | Will be complete as and when a workflow is released. This is to eliminate risk of re-work at the end of the project.
QA Testing | Implementation of pre-configurations and customised elements for workflows | Pending | Will be complete as and when a workflow is released. This is to eliminate risk of re-work at the end of the project.
User Training | Implementation of pre-configurations and customised elements for workflows | Pending | Will be done in two phases, Standard Odoo Training and KSPS training will be provided parallel to the release of workflows)
User Acceptance Test | Implementation of pre-configurations and customised elements for workflows | Pending | Will be complete as and when a workflow is released. This is to eliminate risk of re-work at the end of the project.
Go Live | Implementation of pre-configurations and customised elements for workflows | Pending | 12th October 2018

## Slide 7: Functional Activities - Parallel to KSPS
KP Assembly - Process Discovery, BOM Upload, Gap Analysis Report (Q3, Mid September)
KN Smartcook Stove Distribution Process - Solution to Use Cases, System Gap Analysis, Gap Analysis Report (Q3, 20th August 2018)
KN Inventory Management - All Store Items (Q3, 20th August 2018)
Smartcook Stove Repair - (Q4, Undefined)
KP Maintenance - (Q4, Undefined)

## Slide 8: Questions?

## Slide 9: Thank You